## Risks
Bookify Online Book Store Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2020-05-01 | Users resistance to change | User dont accept any changing | D | 4 | 30% | 0.8 | User | Try to convince the user to change.
2 | 2020-05-01 | Poor project planning | Project plan is not clearly identified | D | 3 | 30% | 0.9 | Plannig&Controll | Rebuild the project plan.
3 | 2020-05-01 | Conflicts between users | May user have different idea about project | D | 5 | 50% | 2.5 | User | Select a leader in users.
4 | 2020-05-01 | Team members lack of specialized skill required by the project | Team member arent expert for the project | D | 5 | 75% | 3.75 | Team | Train team members by a specialist.
5 | 2020-05-01 | Ineffective communication | Communication problem between the team members | D | 5 | 40% | 2 | Communication | Resolves the communication disorder in the team.
6 | 2020-05-01 | Key staff are ill and unavailable at critical times | Key staff can get sick | D | 4 | 10% | 0.4 | Team | Temporary team mate.
7 | 2020-05-01 | Inexperience project managers | Project manager don’t have enough skill and cant lead other membera | I | 4 | 20% | 0.8 | Plannig&Controll | Change project manager or let project manager train itself in a short time.
8 | 2020-05-01 | Immature technology | Trying to develop products with technology that could not be done under the conditions of that day or the community version was not presented. | D | 5 | 45% | 2.25 | Project complexity | The software architect must choose the latest LTS (Long-term support) version of the technology.
9 | 2020-05-01 | Inexperience team members | team member don’t havesuch project experience | D | 4 | 35% | 1.4 | Team | Changig team members with who have experinece.
10 | 2020-05-01 | Unclear system requirements | System requirements are not well established | D | 2 | 40% | 0.8 | Requirements | Derive traceability information to assess requirements change impact; maximize information hiding in the design.
11 | 2020-05-01 | Incorrect system requirements | using wrong system requirements | D | 2 | 40% | 0.8 | Requirements | view system requirement again then select correct one.
12 | 2020-05-01 | Corporate politics with negative effect on the project | having pressure on the management from Corporate politics | D | 1 | 10% | 0.1 | Organizational Environment | Try to deal with politics.
13 | 2020-05-01 | Lack of effective project manage technology | project manage techology not enough for the project | D | 3 | 50% | 1.5 | Planning & Control | Research for new effective manage techology find and use it.
14 | 2020-05-01 | Unstable organizational environment | be concerned about the organization | I | 3 | 15% | 0.45 | Organizational Environment | try to solve concerning about the project by explain aim of project.
15 | 2020-05-01 | Change in organizational management during the project | thereof unexpected thing , need change organizatioal management | I | 2 | 10% | 0.2 | Organizational Environment | changing organizational management or review old one and fix it.
16 | 2020-05-01 | Organization undergoing restructuring during the project | in project organization going to restructuring new organization | I | 3 | 40% | 1.2 | Organizational Environment | Review organization and block new ones
17 | 2020-05-01 | Defective components | Some of components may not work well. | D | 4 | 15% | 0.6 | Planning & Control | Replace potentially defective components with bought-in components of known reliability.
18 | 2020-05-01 | Facility risk | The potential for facility related failures to result in business disruption and losses. | I | 2 | 15% | 0.3 | Organizational Environment | Choosing to avoid actions that triggers that kind of risks.
19 | 2020-05-01 | High level of technical complexity | System is complex | D | 3 | 30% | 0.9 | Planning & Control | Try to change technology.
20 | 2020-05-01 | Project milestone not clearly defined | Milestones are the most critical aspect of the software development cycle. | D | 2 | 65% | 1.3 | Planning & Control | If we realized in progress we need to review milestones and try to define them again clearly.
21 | 2020-05-01 | Incorrect tool requirements | Without tool support, inconsistencies significantly increase and the documented requirements easily get out-of-date. | D | 4 | 25% | 1 | Planning & Control | Use a powerful, yet user-friendly, requirements management tool that enables the storing of requirements metadata.
22 | 2020-05-01 | Inadequate estimation of required resources | The lack of a resource will therefore be a constraint on the completion of the project activity. | D | 4 | 40% | 1.6 | Planning & Control | Managers and leaders should estimate resources more adequately.
23 | 2020-05-01 | The time required to develop the software is underestimated | Schedule risk, the risk that activities will take longer than expected. | D | 5 | 30% | 1.5 | Planning & Control | It is necessary to stick to the timeline for the project.
24 | 2020-05-01 | Project progress not monitored closely enough | If project managers don’t follow project developers might continue on the wrong path. | D | 4 | 50% | 2 | Planning & Control | Project managers should use monitoring applications and job tracking systems and always provide feedback to developers.
25 | 2020-05-01 | Database performance | The database used in the system cannot process as many transactions per second as expected. | D | 5 | 60% | 3 | Planning & Control | Investigate the possibility of buying a higher-performance database.
26 | 2020-05-01 | Legal Risk | Legal risks arise from legal and regulatory obligations, including contract risks and litigation brought against the organization. | I | 3 | 30% | 0.9 | Organizational Environment | Ethical issues are important. It is necessary to be careful.